## new_sheet
| Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Budget 2021 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | April Exchange 2021 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Actuals 2021 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Variance Actuals vs Budget 2021 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Variance Actuals vs April Exchange 2021 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30
0 | Budget Type | Activity | Clinical Study Number | Clinical Study Name | Cost Type | Budget Q1 2021 | Budget Q2 2021 | Budget Q3 2021 | Budget Q4 2021 | Budget FY 2021 | April Reforecast Q1 2021 | April Reforecast Q2 2021 | April Reforecast Q3 2021 | April Reforecast Q4 2021 | April Reforecast FY 2021 | Actuals Q1 2021 | Actuals Q2 2021 | Actuals Q3 2021 | Actuals Q4 2021 | Actuals FY 2021 | Variance Q1 2021 | Variance Q2 2021 | Variance Q3 2021 | Variance Q4 2021 | Variance FY 2021 | Variance Q1 2021 | Variance Q2 2021 | Variance Q3 2021 | Variance Q4 2021 | Variance FY 2021
1 | Development | Clinical | 630CV01C4931 - Pcsk9.CV.HC.Clin.4931-1532 | R727-CL-1532 Neuroccog Study | Internal |  |  |  |  | 0 | 145.8396 | 4.6183 | 0 | 0 | 150.4579 | 100.1749 | 56.8879 |  |  | 157.0628 | 100.1749 | 56.8879 | 0 | 0 | 157.0628 | -45.6647 | 52.2695 | 0 | 0 | 6.6049
2 | Development | Clinical | 630CV01C4931 - Pcsk9.CV.HC.Clin.4931-1532 | R727-CL-1532 Neuroccog Study | External |  |  |  |  | 0 | 605.927 | 173.2899 | 46.9382 | 0 | 826.155 | 163.3879 | 6702.0853 |  |  | 6865.4732 | 263.5629 | 6702.0853 | 0 | 0 | 6865.4732 | -442.5391 | 6528.7954 | -46.9382 | 0 | 6039.3182 | CRO close out costs forecasted in Apr BOD did not include Accounting release of pre-paid expenses to account for competitive enrollment. Close out costs were re-evaluated and updated in the Jun BOD (forecast not shared with Sanofi)
3 | Development | Clinical | 630CV01C4931 - Pcsk9.CV.HC.Clin.4931-1532 Total | R727-CL-1532 Neuroccog Study |  | 0 | 0 | 0 | 0 | 0 | 751.7666 | 177.9082 | 46.9382 | 0 | 976.6129 | 263.5629 | 6758.9732 | 0 | 0 | 7022.536 | 263.5629 | 6758.9732 | 0 | 0 | 7022.536 | -488.2037 | 6581.065 | -46.9382 | 0 | 6045.9231
4 | Development | Clinical | 630CV01C4932- R727-CL-1609 Neurocog (PASS) | R727-CL-1609 Neurocog (PASS) | Internal |  |  |  |  | 0 | 164.1478 | 127.1387 | 0 | 0 | 291.2865 | 137.4581 | 42.6016 |  |  | 180.0597 | 137.4581 | 42.6016 | 0 | 0 | 180.0597 | -26.6898 | -84.5371 | 0 | 0 | -111.2269
5 | Development | Clinical | 630CV01C4932- R727-CL-1609 Neurocog (PASS) | R727-CL-1609 Neurocog (PASS) | External |  |  |  |  | 0 | 38.4142 | 0 | 1873.658 | 0 | 1912.0722 | 67.4641 | 91.0832 |  |  | 158.5473 | 67.4641 | 91.0832 | 0 | 0 | 158.5473 | 29.0499 | 91.0832 | -1873.658 | 0 | -1753.5249
6 | Development | Clinical | 630CV01C4932- R727-CL-1609 Neurocog (PASS) Total | R727-CL-1609 Neurocog (PASS) |  | 0 | 0 | 0 | 0 | 0 | 202.562 | 127.1387 | 1873.658 | 0 | 2203.3587 | 204.9221 | 133.6848 | 0 | 0 | 338.6069 | 204.9221 | 133.6848 | 0 | 0 | 338.6069 | 2.3602 | 6.5461 | -1873.658 | 0 | -1864.7517
7 | Development | Clinical | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen | Internal |  |  |  |  | 0 | 463.2701 | 299.5684 | 305.7192 | 285.6511 | 1354.2088 | 530.7025 | 554.6238 |  |  | 1085.3263 | 530.7025 | 554.6238 | 0 | 0 | 1085.3263 | 67.4324 | 255.0554 | -305.7192 | -285.6511 | -268.8825
8 | Development | Clinical | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen |  | 0 | 0 | 0 | 0 | 0 | 463.2701 | 299.5684 | 305.7192 | 285.6511 | 1354.2088 | 530.7025 | 554.6238 | 0 | 0 | 1085.3263 | 530.7025 | 554.6238 | 0 | 0 | 1085.3263 | 67.4324 | 255.0554 | -305.7192 | -285.6511 | -268.8825
9 | Development | Clinical Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen |  | 0 | 0 | 0 | 0 | 0 | 1417.5987 | 604.6153 | 2226.3154 | 285.6511 | 4534.1804 | 999.1875 | 7447.2818 | 0 | 0 | 8446.4693 | 999.1875 | 7447.2818 | 0 | 0 | 8446.4693 | -418.4112 | 6842.6665 | -2226.3154 | -285.6511 | 3912.2888
10 | Development Total | Clinical Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen |  | 0 | 0 | 0 | 0 | 0 | 1417.5987 | 604.6153 | 2226.3154 | 285.6511 | 4534.1804 | 999.1875 | 7447.2818 | 0 | 0 | 8446.4693 | 999.1875 | 7447.2818 | 0 | 0 | 8446.4693 | -418.4112 | 6842.6665 | -2226.3154 | -285.6511 | 3912.2888
11 | Grand Total | Clinical Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen |  | 0 | 0 | 0 | 0 | 0 | 1417.5987 | 604.6153 | 2226.3154 | 285.6511 | 4534.1804 | 999.1875 | 7447.2818 | 0 | 0 | 8446.4693 | 999.1875 | 7447.2818 | 0 | 0 | 8446.4693 | -418.4112 | 6842.6665 | -2226.3154 | -285.6511 | 3912.2888
12 | Grand Total | Clinical Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen
13 | Grand Total | Clinical Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen
14 | Grand Total | Clinical Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen
15 | 7447281.7647 | Clinical Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen Total | 630GE00G0000 - Pcsk9.Other.Gen.Gen.Gen